HARAMAYA UNIVERSITY | COLLEGE OF COMPUTING AND INFORMATICS
DEPARTMENT OF INFORMATION SCIENCE | POSTGRADUATE RESEARCH PROGRAM

SIX-MONTH MASTER EXECUTION ROADMAP: FROM PROPOSAL TO FINAL DEFENSE
AI-Based Multimodal Deep Learning Early Warning System for Drought, Crop Advisory, and Food Insecurity Prediction in Eastern Ethiopia

| Graduate Researcher: Bona Nasser Abdo (MSc Data Science Candidate) | Principal Advisor: Dr. Million Meshesha (Associate Professor) |
| --- | --- |
| Total Time Horizon: 6 Calendar Months (24 Academic Weeks) | Milestone Gates: Gate 1: Proposal Defense (Month 2) ¦ Gate 2: Final Thesis Defense (Month 6) |

This strategic roadmap outlines the rigorous, week-by-week operational execution plan to complete, defend, and submit the MSc Data Science thesis within a strict six-month timeline. The lifecycle is divided into two major operational phases: Phase I (Proposal Development, Defense & Approval, Months 1–2) and Phase II (Empirical Implementation, Modeling, Writing & Final Thesis Defense, Months 3–6).

1. Master 24-Week Chronological Gantt Schedule

| Phase / Month | Week Span | Core Focus & Milestones | Primary Deliverable / Milestone Gate |
| --- | --- | --- | --- |
| Phase I: Month 1 | Weeks 1–4 | Literature review, 2-page problem brief for Dr. Million, theoretical framing, proposal drafting (Ch 1–3). | Complete Proposal Draft (Chapters 1, 2, 3) |
| Phase I: Month 2 | Weeks 5–8 | Advisor review, DGC submission, proposal slide deck preparation, public defense, post-defense revisions. | GATE 1: Approved Thesis Proposal |
| Phase II: Month 3 | Weeks 9–12 | Automated ingestion (NOAA, CHIRPS, SMAP, MODIS, ERA5), WGS84 woreda alignment, Sc-PDSI climatology engine. | Harmonized Woreda × Month Data Cube |
| Phase II: Month 4 | Weeks 13–16 | Conv1D-LSTM ENSO model, ResNet-50 patch CNN, LSTM sequence, FFT harmonic, Tabular MLP, Gated Cross-Attention. | Trained Model Checkpoints & Baselines |
| Phase II: Month 5 | Weeks 17–20 | Explainable AI (SHAP, Grad-CAM), Neo4j knowledge graph, 4-tier advisory matrix, out-of-sample testing (2024–26). | Empirical Results, XAI & Decision App |
| Phase II: Month 6 | Weeks 21–24 | Full manuscript compilation (Ch 1–5), pre-defense review with Dr. Million, final public defense, hardbound submission. | GATE 2: Final Defended MSc Thesis |

2. Detailed Step-by-Step Weekly Execution Plan

PHASE I: PROPOSAL DEVELOPMENT, DEFENSE & APPROVAL (MONTHS 1–2 / WEEKS 1–8)

Month 1: Problem Formulation, Literature Syntheses & Proposal Drafting

Week 1 (Literature & Theoretical Grounding): Synthesize state-of-the-art literature (Busker et al., 2024; Baye et al., 2026; Abate et al., 2025; Megbar & Tadesse, 2016). Formulate theoretical framework bridging physical climatology to acute food insecurity.

Week 2 (Statement of Problem & Advisor Alignment): Finalize and submit the formal 2-page Statement of the Problem and Data Availability Verification to Dr. Million Meshesha. Incorporate advisor feedback into Chapter 1 (Background, Problem, 3 Research Questions, Objectives).

Week 3 (Methodology & Architecture Drafting): Draft Chapter 2 (Literature Review & Conceptual Framework) and draft Chapter 3 (Study Area profile of Eastern Hararghe, 5-tier architecture, mathematical Sc-PDSI formulations, and Super-Hybrid model design).

Week 4 (Proposal Assembly & Data Audit): Verify zero-credential data ingestion scripts (`data/raw/manifests/dataset.json` with SHA-256 hashes). Assemble complete proposal manuscript (Chapters 1–3, References, Work Plan, Budget).

Month 2: Advisor Iteration, Departmental Submission & Proposal Defense

Week 5 (Advisory Review & One-on-One Critiques): Formal review session with Dr. Million Meshesha. Refine methodology based on supervisory critique (e.g., target label definitions, class imbalance handling, validation boundaries).

Week 6 (Formal DGC Submission & Scheduling): Incorporate all corrections. Submit formal proposal copies and approval sheets to the Department Graduate Committee (DGC) of Information Science.

Week 7 (Proposal Defense Presentation - GATE 1): Develop professional defense slide deck (20 slides: Problem, Research Gaps, 3 RQs, 5-Tier Architecture, Sc-PDSI Physics, Validation). Defend thesis proposal before departmental academic panel.

Week 8 (Post-Defense Revisions & Institutional Clearance): Incorporate examiner comments. Secure official approval signatures from advisors and DGC Chairperson. Obtain formal institutional clearance.

[GATE 1 MILESTONE: PROPOSAL DEFENSE & APPROVAL] MILESTONE GATE 1 ACHIEVED: Officially approved and defended MSc Thesis Proposal registered with the Postgraduate Program Directorate of Haramaya University. Proceed to empirical execution.

PHASE II: EMPIRICAL IMPLEMENTATION, EXPERIMENTAL RIGOR & FINAL DEFENSE (MONTHS 3–6)

Month 3: Automated Ingestion, Harmonization & Physical Climatology Engine

Week 9 (Automated Ingestion & Manifest Security): Deploy automated data connectors downloading verified archives: NOAA PSL (Niño 3.4), CHIRPS v3 (precip), NASA SMAP (soil moisture), MODIS MOD13Q1/MOD11A2, ERA5, SoilGrids, and FEWS NET IPC shapefiles. Verify SHA-256 manifests.

Week 10 (Spatial Alignment & Patch Extraction): Reproject all spatial grids to WGS84 (EPSG:4326). Perform zonal statistics across Eastern Hararghe woreda polygons. Slice standardized 32×32 pixel multi-spectral visual patches centered over woreda centroids.

Week 11 (Physical Climatology & Water Balance Modeling): Code and calibrate the physical two-layer Self-Calibrated Palmer Drought Severity Index (Sc-PDSI) with CAFEC precipitation and Z-index moisture departures. Compute SPI-1, SPI-3, SPI-6, and VCI rasters.

Week 12 (Master Analytical Data Cube Assembly): Assemble master analytical table structured as Woreda × Month. Generate 1-, 2-, 3-, and 6-month historical lags strictly using antecedent observations prior to timestamp t (zero future data leakage).

Month 4: Deep Learning Development, Baseline Training & Fusion Modeling

Week 13 (Conv1D-LSTM ENSO Teleconnection Modeling): Train and calibrate the Conv1D-LSTM oceanic teleconnection forecaster. Evaluate Niño 3.4 SST anomaly predictions across 1–12 leads against persistence and ridge baselines.

Week 14 (Specialized Modality Encoder Construction): Build and pre-train the four specialized encoders: (a) ResNet-50 spatial patch CNN, (b) 12-month recurrent LSTM temporal sequence branch, (c) Fast Fourier Transform (FFT) harmonic spectral branch, and (d) structured tabular MLP.

Week 15 (Cross-Attention Fusion & Multi-Task Training): Implement the Multimodal Gated Cross-Attention Fusion Engine. Connect multi-task heads for Drought Hazard P(SPI-3<=-1), Crop Risk P_adj, and FEWS NET / IPC Acute Food Insecurity (Phases 1–5). Apply Focal Loss (gamma=2.0) and class-weighted cross-entropy.

Week 16 (Baseline Training & Comparative Benchmarking): Train classical machine learning baselines (Logistic Regression, Random Forest, XGBoost) and unimodal deep networks under identical chronological splits (2015–2021 train, 2022–2023 validation). Record comparative performance tables.

Month 5: Explainable AI, Knowledge Graph, Decision Platform & Evaluation

Week 17 (Explainable AI - SHAP & Grad-CAM Implementation): Implement Explainable AI pipelines: compute SHAP feature attributions (global bar charts & local waterfall plots) for tabular features; generate Grad-CAM heatmaps for satellite visual patches; compute temporal lag attributions.

Week 18 (Neo4j Semantic Knowledge Graph Modeling): Construct the Neo4j Semantic Knowledge Graph. Ingest woredas, crops, climate observations, hazard events, and IPC phases. Implement Cypher queries for multi-hazard cascading vulnerability reasoning.

Week 19 (Prescriptive Advisory & IEK Consensus Engine): Calibrate biological crop sensitivity multipliers (s) for sorghum, maize, haricot bean, wheat, and tef. Map adjusted risks to the 4-tier prescriptive advisory matrix. Implement the Bi-Directional IEK Consensus Engine.

Week 20 (Independent Hindcasting & Honest Lead Validation): Execute independent out-of-sample hindcasting on the strictly withheld 2024–2026 test window. Compute Brier Skill Scores (BSS), ROC-AUC, PR-AUC, Macro F1, and reliability calibration curves. Enforce the 'Honest Lead Horizon' principle.

Month 6: Manuscript Compilation, Advisory Review & Final Thesis Defense

Week 21 (Complete Thesis Manuscript Drafting): Compile complete Master Thesis manuscript: Chapter 1 (Introduction), Chapter 2 (Literature Review), Chapter 3 (Methodology), Chapter 4 (Results & In-Depth Discussion with 17+ tables and figures), Chapter 5 (Conclusions & Recommendations), and Appendices A–E.

Week 22 (Advisory Review, Revisions & Pre-Defense Clearance): Comprehensive manuscript review with Dr. Million Meshesha. Conduct mock defense presentations. Revise all chapters based on detailed advisory critique.

Week 23 (FINAL MSC THESIS DEFENSE - GATE 2): Deliver formal public defense presentation before Internal Examiner, External Examiner, DGC Chairperson, and academic community. Present live decision-support dashboard and empirical validation results.

Week 24 (Final Corrections, Sign-Off & Institutional Submission): Incorporate minor examiner corrections. Obtain official defense approval signatures. Prepare final hardbound copies and electronic submission to Haramaya University Library and Institutional Repository.

[GATE 2 MILESTONE: DEGREE COMPLETION & FINAL SUBMISSION] MILESTONE GATE 2 ACHIEVED: Final Master of Science degree requirements fulfilled. Completed, defended, and submitted MSc Data Science Thesis with open-source codebase and peer-reviewed journal draft ready for submission.

3. Technical & Academic Risk Mitigation Matrix

| Potential Execution Risk | Impact / Probability | Proactive Mitigation Strategy |
| --- | --- | --- |
| GPU compute bottlenecks or out-of-memory errors during multimodal patch training | High / Medium | Utilize mixed-precision (FP16) training, gradient accumulation, and batch size auto-scaling; leverage Google Colab Pro / Kaggle GPU instances. |
| Delayed or missing food-insecurity labels from official agencies | High / Low | Supervised food-security modeling is strictly bounded to verified 2020–2026 FEWS NET shapefiles; physical Sc-PDSI/SPI targets cover the full 2015–2026 window. |
| Advisor availability constraints or delayed review cycles | Medium / Medium | Maintain strict dekadal progress memos, shared Overleaf/Word cloud documents, and bi-weekly milestone check-ins with Dr. Million Meshesha. |
| Class imbalance distorting high-risk drought and IPC Phase 4/5 predictions | High / High | Apply Focal Loss (gamma=2.0), class-weighted cross-entropy, and SMOTE exclusively within training folds; evaluate via PR-AUC and Macro F1. |